## Cover
Business Analysis Plan
Project Name | Waterfront Realty Site
Author | Natasha Kordonska
Version | 1
Date | 2024-11-30
Revision History
Revision # | Content Changed | Change Date
1 | Version for sign-off | 2024-11-30

## Requirements Stakeholder List
Requirements Stakeholder List
Name | Role | Approve/ Review Requirements
Jane Smith, VP of Sales | Business Sponsor | Approve
John Simm, Director of Sales | Business Owner | Review
Joe Fresh, Agent | SME | Review
Angela Wick, Agent | SME | Review
Andrew Zolof, Agent | SME | Review
Tim Clark, PM | Project Manager | Review
Mandy Moore, QA Manager | Quality Assurance | Review
Julia Roberts, Sr. Developer | Technology Lead | Approve
Tom Cruise, Developer | Developer | Review
Natasha Kordonska, Sr. BA Manager | BA Manager | Approve

## Approach and Assumptions
Requirements Approach and Assumptions
Requirements Approach
Elicitation through document analysis, interviews, workshops
Analysis with scope analysis, business process diagram, use case diagram, use case, data, business rules, UI
Traceability is forward: Problem / Opportunity --> Scope Item--> Business Process --> Use case and related detailed requirements or Non-functional requirements
Requirements are communicated through workshops, which are used for both elicitation and review processes.
Requirements will be stored on SharePoint and in Jira & Confluence
Plan Assumptions | Impact | Mitigation
All business stakeholders are available for elicitation and review activities | Delays in the elicitation and progression of requirements | Confirm with business sponsor
All technology stakeholders are available for elicitation and review activities | Delayed assessment of technology capabilities | Confirm with Project Manager

## Requirements Work Plan
Requirements Work Plan
# | Task and Milestones | Effort, hrs | Resources | Technique
1 | Iteration 1 - Stakeholder Requirements
1.1 | Review Business Needs | 4 | Project Kick-Off Materials | Document Analysis
1.2 | Conduct interview with business owner | 5 | Business Owner | Interview
1.3 | Develop business context diagram and user stories to support the stakeholder requirements elicitation session. | 2 | Interview notes | BCD, User Stories
1.4 | Elicit stakeholder requirements | 3 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Elicitation Workshop
1.5 | Revise and validate stakeholder requirements in collaboration with the BA Manager. | 2 | BA Manager | Review
1.6 | Conduct a review session for stakeholder requirements and make updates as necessary. | 2 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Review Workshop
1.7 | Approval of stakeholder requirements | 2 | Business Owner, Technology Lead, BA Manager | Review
2 | Iteration 2 - Business Process Diagrams
2.1 | Analyze the current state and draft future state business processes for Create Listing, Update Listing, Delete Listing, Book Showing, and Request More Info. | 5 | Current state process documentation | Document Analysis, BPM
2.2 | Elicitation session for business processes | 4 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Elicitation Workshop
2.3 | Revise and review Business Process Diagrams with the BA Manager, then distribute them based on feedback | 2 | BA Manager | Review
2.4 | Review future state business processes and make updates as necessary. | 2 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Review Workshop
3 | Iteration 3 - Use Case Diagram and NFR
3.1 | Create a draft Use Case Diagram for the Waterfront Realty website. | 3 | Business Analyst | UCD
3.2 | Trace High Level Requirements to Use Cases as applicable | 3 | Business Analyst | Traceability
3.3 | Elicitation session for Use Case Diagram | 6 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Elicitation Workshop
3.4 | Revise the Use Case Diagram, review it with the BA Manager, and distribute it following the feedback. | 4 | BA Manager | Review
3.5 | Review Use Case Diagram and make updates as necessary. | 1 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Review Workshop
3.6 | Prepare draft NFR | 3 | Existing documentation, standard templates | NFR, Document Analysis
3.7 | Elicitation for NFR | 3 | Technology Lead, Business Owner | Interview
3.8 | Update NFR, review with BA Manager and distribute for review | 1 | BA Manager | Review
4 | Iteration 4 - Use Case, Data, Rules, UI for UC01 - Manage Listing
4.1 | Prepare draft for UC01 including data, rules, messages, UI list, UI storyboard, UI mockup | 18 | Business Analyst, SMEs | UC, Data Dictionary, Business Rules, Prototyping
4.2 | Elicitation sessions for UC01 including data, rules, messages, UI list, UI storyboard, UI mockup | 7 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Requirements Workshop
4.3 | Update, review with BA Manager and distribute UC01 including data, rules, messages, UI list, UI storyboard, UI mockup | 6 | BA Manager | Review
4.4 | Review sessions for UC01 including data, rules, messages, UI list, UI storyboard, UI mockup, and make updates as necessary. | 2 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Review Workshop
5 | Iteration 5 - Use Case, Data, Rules, UI for UC02-View Listing, UC03-Request Showing, UC04-Request More Info
5.1 | Prepare drafts for UC02, UC03 and UC04, including data, business rules, messages, UI elements, UI storyboards, and UI mockups. | 18 | Business Analyst, SMEs | UC, Data Dictionary, Business Rules, Prototyping
5.2 | Conduct elicitation sessions for UC02, UC03 and UC04, covering data, business rules, messages, UI elements, UI storyboards, and UI mockups. | 7 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Requirements Workshop
5.3 | Update, review with BA Manager and distribute UC02 UC03 and UC04, including data, rules, messages, UI list, UI storyboards, UI mockups | 6 | BA Manager | Review
5.4 | Review sessions for UC02, UC03 and UC04, including data, rules, messages, UI list, UI storyboards, UI mockups, and make updates as necessary. | 2 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Review Workshop
6 | Iteration 6 - Use Case, Data, Rules, UI for UC05-Request Report, UC06-Send Report, UC07-Archive Listing
6.1 | Prepare draft for UC05, UC06 and UC07, including data, rules, messages, UI list, UI storyboards, UI mockups | 18 | Business Analyst, SMEs | UC, Data Dictionary, Business Rules, Prototyping
6.2 | Elicitation sessions for UC05, UC06 and UC07, including data, rules, messages, UI list, UI storyboards, UI mockups | 7 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Requirements Workshop
6.3 | Update, review with BA Manager and distribute UC05, UC06 and UC07, including data, rules, messages, UI list, UI storyboards, UI mockups | 6 | BA Manager | Review
0.4 | Review UC05, UC06 and UC07, including data, rules, messages, UI list, UI storyboards, UI mockups and make updates as necessary. | 2 | Business Owner, SMEs, PM, QA, Technology Lead, Developer, BA Manager | Review Workshop
6.5 | Update traceability to Solution Requirements | 4 | BA Manager | Traceability
6.6 | Obtain Approval on Solution Requirements | 1 | Business Owner, Technology Lead, BA Manager | Review